## Gantt Chart
ID | WBS | Task | Owner | Start | End | Dur (days) | Dependencies | 09/18 | 09/19 | 09/20 | 09/21 | 09/22 | 09/23 | 09/24 | 09/25 | 09/26 | 09/27 | 09/28 | 09/29 | 09/30 | 10/01 | 10/02 | 10/03 | 10/04 | 10/05 | 10/06 | 10/07 | 10/08 | 10/09 | 10/10 | 10/11 | 10/12 | 10/13 | 10/14 | 10/15
P1 | 1.1/2.1 | Task breakdown and role assignment (read case study) | All | 2026-09-18 | 2026-09-18 | 1 | - | bar: 09/18
P2 | 1.1 | Draft Project Charter + feasibility analysis | Cao Yang / Chen Shuai / Zhang Runze | 2026-09-19 | 2026-09-19 | 1 | P1
P3 | 1.3 | Kick-off meeting + meeting minutes | All | 2026-09-20 | 2026-09-20 | 1 | P2
P4 | 1.2 | WBS decomposition + task dependency mapping | Zhang Runze / Zhou Kunpeng | 2026-09-21 | 2026-09-21 | 1 | P3 | bar: 09/21
P5 | 1.2 | Scheduling, Gantt chart + cross-review finalisation | Zhou Kunpeng / All | 2026-09-22 | 2026-09-22 | 1 | P4 | bar: 09/22
R1 | 2.1 | Deep case analysis, derive user stories | Chen Shuai | 2026-09-23 | 2026-09-24 | 2 | P5 | bar: 09/23 to 09/24
R2 | 2.2 | Jira setup + build product backlog | Chen Shuai / Cao Yang | 2026-09-25 | 2026-09-25 | 1 | R1 | bar: 09/25
R3 | 2.3 | Sprint backlog selection (8–15 stories) | All | 2026-09-26 | 2026-09-27 | 2 | R2
D1 | 3.1 | Data model design (four entities) | Zhang Runze | 2026-09-28 | 2026-09-29 | 2 | R3 | bar: 09/28 to 09/29
D2 | 3.2 | Business rule design (guardian validation) | Zhang Runze / Chen Shuai | 2026-09-29 | 2026-09-29 | 1 | D1 | bar: 09/29
D3 | 3.3 | README and directory structure design | Zhang Runze | 2026-09-30 | 2026-09-30 | 1 | D1 | bar: 09/30
DEV1 | 4.1 | Member CRUD, persistence, search | Zhou Kunpeng | 2026-10-01 | 2026-10-03 | 3 | D1 | bar: 10/01 to 10/02
DEV2 | 4.2 | Guardian entity + one-to-many links + sync | Zhang Runze | 2026-10-02 | 2026-10-04 | 3 | D2 | bar: 10/02
DEV3 | 4.3 | Season registration + status flow + guardian validation | Chen Shuai | 2026-10-04 | 2026-10-06 | 3 | D2 | bar: 10/05 to 10/06
DEV4 | 4.4 | Team creation + add/move/remove players + roster | Zhang Runze | 2026-10-06 | 2026-10-08 | 3 | DEV1 | bar: 10/06 to 10/08
DEV5 | 4.5 | Views development (roster/history/juniors) | Zhou Kunpeng | 2026-10-08 | 2026-10-09 | 2 | DEV3 | bar: 10/08 to 10/09
T1 | 5.1 | Unit automated tests (guardian rule focus) | Zhang Runze | 2026-10-09 | 2026-10-10 | 2 | DEV2/DEV3 | bar: 10/09
T2 | 5.2 | End-to-end tests (acceptance criteria coverage) | Chen Shuai / Zhou Kunpeng | 2026-10-11 | 2026-10-11 | 1 | T1
T3 | 5.3 | Clean-checkout verification (fresh clone run) | All | 2026-10-12 | 2026-10-12 | 1 | T2 | bar: 10/12
H1 | 6.1 | GitHub maintenance + PR review (ongoing) | Zhang Runze | 2026-10-01 | 2026-10-12 | 12 | D3 | bar: 10/01 to 10/02; 10/05 to 10/09; 10/12
H2 | 6.2 | Confluence documentation (ongoing) | Chen Shuai | 2026-10-08 | 2026-10-13 | 6 | D1 | bar: 10/08 to 10/09; 10/12 to 10/13
H3 | 6.3 | Handover documentation (6 sections) | Cao Yang / All | 2026-10-13 | 2026-10-14 | 2 | T3 | bar: 10/13 to 10/14
C1 | 7.1 | Deliverables consolidation and finalisation | Cao Yang | 2026-10-14 | 2026-10-14 | 1 | H3 | bar: 10/14
C2 | 7.2 | Project retrospective + next-sprint recommendations | All | 2026-10-15 | 2026-10-15 | 1 | C1 | bar: 10/15
▲ Milestones
M1 |  | Project Kick-off Complete |  | 2026-09-20 | bar: 09/20
M2 |  | Planning Documents Approved |  | 2026-09-22 | bar: 09/22
M3 |  | Requirements Approved (Sprint Backlog Set) |  | 2026-09-27 | bar: 09/27
M4 |  | Design Approved |  | 2026-09-30 | bar: 09/30
M5 |  | Development Complete |  | 2026-10-09 | bar: 10/09
M6 |  | Testing Complete (DoD Met) |  | 2026-10-12 | bar: 10/12
M7 |  | Delivery Preparation Complete |  | 2026-10-14 | bar: 10/14
M8 |  | Project Closure |  | 2026-10-15 | bar: 10/15

## Task List
ID | WBS | Task | Owner | Start | End | Dur (days) | Dependencies | Phase
P1 | 1.1/2.1 | Task breakdown and role assignment (read case study) | All | 2026-09-18 | 2026-09-18 | 1 | - | Planning
P2 | 1.1 | Draft Project Charter + feasibility analysis | Cao Yang / Chen Shuai / Zhang Runze | 2026-09-19 | 2026-09-19 | 1 | P1 | Planning
P3 | 1.3 | Kick-off meeting + meeting minutes | All | 2026-09-20 | 2026-09-20 | 1 | P2 | Planning
P4 | 1.2 | WBS decomposition + task dependency mapping | Zhang Runze / Zhou Kunpeng | 2026-09-21 | 2026-09-21 | 1 | P3 | Planning
P5 | 1.2 | Scheduling, Gantt chart + cross-review finalisation | Zhou Kunpeng / All | 2026-09-22 | 2026-09-22 | 1 | P4 | Planning
R1 | 2.1 | Deep case analysis, derive user stories | Chen Shuai | 2026-09-23 | 2026-09-24 | 2 | P5 | Requirements
R2 | 2.2 | Jira setup + build product backlog | Chen Shuai / Cao Yang | 2026-09-25 | 2026-09-25 | 1 | R1 | Requirements
R3 | 2.3 | Sprint backlog selection (8–15 stories) | All | 2026-09-26 | 2026-09-27 | 2 | R2 | Requirements
D1 | 3.1 | Data model design (four entities) | Zhang Runze | 2026-09-28 | 2026-09-29 | 2 | R3 | Design
D2 | 3.2 | Business rule design (guardian validation) | Zhang Runze / Chen Shuai | 2026-09-29 | 2026-09-29 | 1 | D1 | Design
D3 | 3.3 | README and directory structure design | Zhang Runze | 2026-09-30 | 2026-09-30 | 1 | D1 | Design
DEV1 | 4.1 | Member CRUD, persistence, search | Zhou Kunpeng | 2026-10-01 | 2026-10-03 | 3 | D1 | Development
DEV2 | 4.2 | Guardian entity + one-to-many links + sync | Zhang Runze | 2026-10-02 | 2026-10-04 | 3 | D2 | Development
DEV3 | 4.3 | Season registration + status flow + guardian validation | Chen Shuai | 2026-10-04 | 2026-10-06 | 3 | D2 | Development
DEV4 | 4.4 | Team creation + add/move/remove players + roster | Zhang Runze | 2026-10-06 | 2026-10-08 | 3 | DEV1 | Development
DEV5 | 4.5 | Views development (roster/history/juniors) | Zhou Kunpeng | 2026-10-08 | 2026-10-09 | 2 | DEV3 | Development
T1 | 5.1 | Unit automated tests (guardian rule focus) | Zhang Runze | 2026-10-09 | 2026-10-10 | 2 | DEV2/DEV3 | Testing
T2 | 5.2 | End-to-end tests (acceptance criteria coverage) | Chen Shuai / Zhou Kunpeng | 2026-10-11 | 2026-10-11 | 1 | T1 | Testing
T3 | 5.3 | Clean-checkout verification (fresh clone run) | All | 2026-10-12 | 2026-10-12 | 1 | T2 | Testing
H1 | 6.1 | GitHub maintenance + PR review (ongoing) | Zhang Runze | 2026-10-01 | 2026-10-12 | 12 | D3 | Delivery
H2 | 6.2 | Confluence documentation (ongoing) | Chen Shuai | 2026-10-08 | 2026-10-13 | 6 | D1 | Delivery
H3 | 6.3 | Handover documentation (6 sections) | Cao Yang / All | 2026-10-13 | 2026-10-14 | 2 | T3 | Delivery
C1 | 7.1 | Deliverables consolidation and finalisation | Cao Yang | 2026-10-14 | 2026-10-14 | 1 | H3 | Closure
C2 | 7.2 | Project retrospective + next-sprint recommendations | All | 2026-10-15 | 2026-10-15 | 1 | C1 | Closure