Work Breakdown Structure (WBS) and Key Milestones

Warrigal Park Football Club Member Registration & Team Roster System · Assignment 3 / Module 1

1. Decomposition Rules

Deliverable-oriented: the WBS decomposes deliverables and work packages, not process activities such as meetings or emails.

Levels: Level 1 is the whole project; Level 2 is the seven phases (Project Management / Requirements / Design / Development / Testing / Delivery Preparation / Project Closure); Level 3 is individual work packages.

8/80 rule: each work package is sized between 8 and 80 hours.

Project Management is a separate branch, approximately 12% of total effort.

2. WBS Structure (tree)

Level 1  Warrigal Park FC Member Registration & Team Roster System

├─ 1.0 Project Management (Owner: Cao Yang) — approx. 12% of total effort

│   ├─ 1.1 Project initiation documents (Project Charter, meeting minutes) — Cao Yang / Chen Shuai

│   ├─ 1.2 WBS, milestones and Gantt chart planning — Zhou Kunpeng

│   └─ 1.3 Team meetings, risk tracking, Confluence record maintenance — Cao Yang

├─ 2.0 Requirements Analysis and Backlog Management (Owner: Chen Shuai)

│   ├─ 2.1 Case study analysis (3 interviews, 3 paper documents, association circular), derive all user stories — Chen Shuai

│   ├─ 2.2 Jira setup, build the product backlog — Chen Shuai / Cao Yang

│   └─ 2.3 Sprint backlog selection (8–15 stories, 1–2 epics, set the committed iteration scope) — All

├─ 3.0 System Design (Owner: Zhang Runze)

│   ├─ 3.1 Data model design (Member / Guardian / Registration / Team entities and relationships) — Zhang Runze

│   ├─ 3.2 Business rule design (mandatory guardian validation for players under 18) — Zhang Runze / Chen Shuai

│   └─ 3.3 README and project directory structure design — Zhang Runze

├─ 4.0 Development (Owner: Zhang Runze, with Chen Shuai / Zhou Kunpeng)

│   ├─ 4.1 Member CRUD, persistence, search by name (incl. same-name) — Zhou Kunpeng

│   ├─ 4.2 Guardian entity, one-to-many links, sync updates across children — Zhang Runze

│   ├─ 4.3 Season registration, status flow (started/complete/withdrawn), guardian rule validation — Chen Shuai

│   ├─ 4.4 Team creation, place/move/remove players, rosters — Zhang Runze

│   └─ 4.5 Views (roster + contacts, registration history, guardian’s juniors) — Zhou Kunpeng

├─ 5.0 Testing (Owner: Zhang Runze)

│   ├─ 5.1 Unit automated tests (focus on the junior guardian rule) — Zhang Runze

│   ├─ 5.2 End-to-end tests covering each story’s acceptance criteria — Chen Shuai / Zhou Kunpeng

│   └─ 5.3 Clean-checkout verification (run from a fresh clone using README alone) — All

├─ 6.0 Delivery Preparation (Owner: Cao Yang)

│   ├─ 6.1 GitHub repository maintenance, branch management, PR review workflow — Zhang Runze

│   ├─ 6.2 Confluence documentation: business assumptions, decision records — Chen Shuai

│   └─ 6.3 Sprint-close handover documentation (6-section structure) — Cao Yang / All

└─ 7.0 Project Closure (Owner: Cao Yang)

├─ 7.1 Consolidation and finalisation of all deliverables — Cao Yang

└─ 7.2 Retrospective, known limitations, next-iteration recommendations — All

3. Work Package Details (Owner + Estimated Duration)

| WBS ID | Work Package | Owner | Est. Duration |
| --- | --- | --- | --- |
| 1.1 | Project initiation documents (charter, minutes) | Cao Yang / Chen Shuai | 2 days |
| 1.2 | WBS, milestones and Gantt chart planning | Zhou Kunpeng | 3 days |
| 1.3 | Team meetings, risk tracking, Confluence maintenance | Cao Yang | Ongoing |
| 2.1 | Case study analysis, derive all user stories | Chen Shuai | 2 days |
| 2.2 | Jira setup, build product backlog | Chen Shuai / Cao Yang | 1 day |
| 2.3 | Sprint backlog selection (8–15 stories) | All | 2 days |
| 3.1 | Data model design (four entities and relationships) | Zhang Runze | 2 days |
| 3.2 | Business rule design (guardian validation) | Zhang Runze / Chen Shuai | 1 day |
| 3.3 | README and directory structure design | Zhang Runze | 1 day |
| 4.1 | Member CRUD, persistence, search | Zhou Kunpeng | 3 days |
| 4.2 | Guardian entity, one-to-many links, sync updates | Zhang Runze | 3 days |
| 4.3 | Season registration, status flow, guardian rule validation | Chen Shuai | 3 days |
| 4.4 | Team creation, place/move/remove players, rosters | Zhang Runze | 3 days |
| 4.5 | Views development (roster/history/juniors) | Zhou Kunpeng | 2 days |
| 5.1 | Unit automated tests (guardian rule focus) | Zhang Runze | 2 days |
| 5.2 | End-to-end tests (acceptance criteria coverage) | Chen Shuai / Zhou Kunpeng | 1 day |
| 5.3 | Clean-checkout verification (fresh clone run) | All | 1 day |
| 6.1 | GitHub maintenance, branch management, PR review | Zhang Runze | Ongoing |
| 6.2 | Confluence documentation (assumptions & decisions) | Chen Shuai | Ongoing |
| 6.3 | Handover documentation (6 sections) | Cao Yang / All | 2 days |
| 7.1 | Deliverables consolidation and finalisation | Cao Yang | 1 day |
| 7.2 | Retrospective, known limitations, next-sprint recommendations | All | 1 day |

4. Key Milestones (8)

| ID | Milestone | Acceptance Criteria / Deliverable | Planned Date |
| --- | --- | --- | --- |
| M1 | Project Kick-off Complete | Kick-off meeting held, minutes finalised | 2026-09-20 |
| M2 | Planning Documents Approved | Four planning documents (charter, WBS, Gantt chart) cross-reviewed and approved | 2026-09-22 |
| M3 | Requirements Approved | Sprint backlog (8–15 user stories) defined and approved in Jira | 2026-09-27 |
| M4 | Design Approved | Data model and business rule design completed and reviewed | 2026-09-30 |
| M5 | Development Complete | All committed stories merged to GitHub (story-named branches, PR reviews done) | 2026-10-09 |
| M6 | Testing Complete (DoD Met) | All automated tests pass, clean-checkout verification succeeds, no critical defects | 2026-10-12 |
| M7 | Delivery Preparation Complete | Handover documentation (6 sections) and Confluence records finalised | 2026-10-14 |
| M8 | Project Closure | Retrospective complete, all deliverables submitted | 2026-10-15 |

5. Project Timeline

| Phase | Time Range | Description |
| --- | --- | --- |
| Planning Phase | 2026-09-18 ~ 2026-09-22 (5 days) | Roles, charter, kick-off, WBS, Gantt chart; outputs the four planning documents |
| Scrum Sprint (Dev + Test) | 2026-09-23 ~ 2026-10-13 (3 weeks) | Backlog definition → design → development → testing; sprint commits 8–15 stories |
| Closure Phase | 2026-10-14 ~ 2026-10-15 | Handover documentation, retrospective, final deliverable submission |