Project Charter

Warrigal Park Football Club Member Registration & Team Roster System · Assignment 3 / Module 1

1. Project Overview

| Field | Details |
| --- | --- |
| Project Name | Warrigal Park FC Member Registration & Team Roster System |
| Project ID | ASG3-M1 (Software Project Management course, Assignment 3) |
| Sponsor | Course team (simulating the Warrigal Park Football Club Committee) |
| Project Manager | Cao Yang |
| Project Team | Cao Yang, Chen Shuai, Zhang Runze, Zhou Kunpeng |
| Date / Version | 2026-09-20 / V1.0 |

2. Background and Business Value (Why)

2.1 Business Background

Warrigal Park Football Club Inc. is a community football club based at Warrigal Park, 60 Kluver Street, Bald Hills, on Brisbane’s northern edge, and has fielded teams every season since 1978. In 2026 the club registered 640 players — 520 juniors from Under 6 to Under 18 and 120 seniors — fielding 47 teams in the Northside Football Association’s competitions. The club is run almost entirely by volunteers, with registration happening on two Saturdays in February.

The current registration flow relies on paper forms, a 43-column Excel master spreadsheet, a second data-entry pass into the association’s PlayRegister system, and manual distribution of age-group lists to the junior coordinator. This flow suffers from duplicate data entry, poor data quality, insurance compliance risk and inefficient reporting.

2.2 Problems to Solve

The same registration details are typed multiple times (master spreadsheet, PlayRegister, age-group lists), inviting errors.

Forms come back unreadable or with the guardian section blank; siblings are entered twice and players with the same name are confused.

In 2024 a player took the field whose registration had not gone through, raising an insurance liability risk (Association circular item 4).

Registration statistics are counted by hand, and team nominations to the association are chronically submitted at the last minute (1 March).

2.3 Measurable Success Criteria

| ID | Measurable Success Criterion |
| --- | --- |
| S1 | The system supports full create/read/update plus deactivate/withdraw operations across the five capabilities: Member, Guardian, Registration, Team & Roster, Views |
| S2 | The guardian business rule is enforced: a registration for a player under 18 with no linked guardian must be refused with a reason |
| S3 | A single guardian can be linked to multiple junior players; updating the guardian’s contact details updates all linked children’s records |
| S4 | Every committed user story satisfies the case study’s Definition of Done (GitHub branch commits, PR review, automated tests, clean-checkout run, no critical defects, Jira/Confluence sync) |
| S5 | A runnable version is delivered by 6 February 2026 (before the sign-on days) |
| S6 | The system costs nothing to run (GitHub Free, Jira/Confluence education licence, Python open-source stack, no server required) |

3. Project Scope (What)

3.1 In-Scope

| Capability | Description |
| --- | --- |
| Member | Create, find, update and deactivate player records; store at minimum a name, date of birth and contact details; data persisted; search by name (including same-name matches) |
| Guardian | Create, find and update guardian records; one guardian can be linked to multiple junior players; updating a guardian’s information automatically syncs all linked children |
| Registration | Players register for a season; records season, age group and status (started / complete / withdrawn); create, amend, view and withdraw registrations; players under 18 must have a linked guardian to complete registration, while players aged 18+ register in their own right without a guardian |
| Team & Roster | Create a team for a season (name + age group); registered players can be placed into, moved between and removed from teams; list a team’s full roster |
| Views | A team’s roster with a contact for each player; a member’s registration history; the juniors linked to a given guardian |
| Project Deliverables | GitHub repository, Jira product backlog, Confluence decision and assumption records, one 3-week Scrum sprint delivery, handover documentation (6-section structure) |

3.2 Out-of-Scope (moved to the product backlog; not built this iteration)

| Excluded Item | Description |
| --- | --- |
| Fees & Finance | All financial features: fees, payments, discounts, volunteer levy, fee reports |
| PlayRegister Integration | Import/export or integration with the association system (our system sits alongside PlayRegister; it does not replace it) |
| Compliance Checks | Blue card / Working with Children Check (WWCC) expiry tracking and compliance checks |
| Squad & Age Validation | Enforcing squad size limits, checking that a player’s age matches the age group they are placed in |
| Match-related | Fixtures, results and ladders |
| Other Items | Canteen roster, uniform and kit ordering, SMS/email notifications, families registering themselves online, the club website |

3.3 Budget and Constraints

| Dimension | Details |
| --- | --- |
| Budget | $0: free tools only (GitHub Free, Jira/Confluence education licence, Python ecosystem) |
| Time Constraint | A runnable version must be delivered by 6 February 2026 (hard requirement before club sign-on); this semester: 2 weeks of planning + 3 weeks of sprint |
| Technical Constraint | Deliverable as a Python command-line application or a web application — either is acceptable; no deployment required; handover is code + README run instructions |
| Business Rule Constraint | A player under 18 cannot complete registration unless at least one guardian record is linked; otherwise the registration is refused with a reason |
| Compliance Constraint | Minors’ privacy must be protected; handover documents and sample data must be fictitious — never use real children’s details |
| Team Constraint | 4-person team, one person may hold multiple roles; work allocated in 8–80 hour work packages |

4. Stakeholders (Who)

4.1 Key Stakeholders

| Stakeholder | Role | Interests and Expectations |
| --- | --- | --- |
| Vanessa Ostrowski | Club Registrar (primary user of the software) | Data quality, eliminating duplicate entry; junior registrations must have a linked guardian, and guardian changes must sync to all children; minors’ privacy; usable by 6 February |
| Danny Sok | Junior Coordinator (U13 Girls coach) | View players by age group, move players between teams, maintain team lists; quick access to guardian contacts; fast operation (used late at night in February) |
| Robyn Iyer | Club President | Registration totals (by age group and gender, vs last year); timely team nominations to the association; zero cost |
| Association (NFA) | External constraint | PlayRegister is mandatory for insurance; nominations due 1 March; under-18 consent must be held (not directly building the system) |

4.2 Project Team

| Name | Role | Key Responsibilities |
| --- | --- | --- |
| Cao Yang | Project Manager (PM) | Overall progress control, chair the Kick-off, owner of the Project Charter, milestone and risk tracking |
| Chen Shuai | Business/Requirements Lead + Scribe | Requirements analysis, scope definition, stakeholder expectation mapping, meeting minutes, Confluence decision records |
| Zhang Runze | Technical Lead | Feasibility assessment, WBS technical decomposition, data model and business rule design, testing strategy |
| Zhou Kunpeng | Scheduling Lead | Gantt chart, milestone scheduling, task dependency and resource overload checks |

5. Feasibility Conclusions

| Dimension | Conclusion | Key Assumption / Basis |
| --- | --- | --- |
| Technical | Feasible | A small CRUD application plus one genuine domain rule (junior guardian validation); implementable in Python CLI or web; automated tests and Git version control are achievable; assumes the team has basic Python programming skills |
| Economic | Feasible | Free open-source tool stack (GitHub Free, Jira/Confluence education licence); no server or paid software, satisfying the club’s “it can’t cost anything” constraint |
| Operational | Feasible | Handover is code + README + handover documentation, runnable locally by volunteers; the system sits alongside PlayRegister and replaces the internal Excel master and Danny’s copies |
| Schedule | Feasible | 2 weeks of planning + 3 weeks of sprint; sprint scope trimmed to 8–15 user stories, the rest stays visible and prioritised in the product backlog |

6. High-Level Risks (3–5)

| Risk | Impact | Mitigation |
| --- | --- | --- |
| R1: Guardian business rule implemented incorrectly (allowing a junior registration with no guardian) | Violates the club’s core rule; compliance risk | Standalone automated test for this rule; DoD requires at least one guardian-rule test case per related story |
| R2: Scope creep (fees, SMS, fixtures etc. pulled into the iteration) | Committed scope out of control; missed delivery | Out-of-Scope list explicit in the charter; sprint review gate; new requests go to the product backlog |
| R3: Team scheduling conflicts; sprint tasks not finished on time | Delivery slip | Sprint backlog limited to 8–15 stories with core capabilities prioritised; 8–80 hour work packages; escalate to PM early |
| R4: Documentation and code drift; fresh environment cannot run from README | DoD not met; failed handover | DoD enforces clean-checkout verification; README is the single source of truth; no undocumented local dependencies |
| R5: Case information scattered (interviews, paper documents, association circular); requirement misinterpretation | Acceptance criteria diverge from real business needs | Cross-check the three interviews and three paper documents; record every business assumption in Confluence and review them |

7. Milestones and Deliverables Overview

The project has eight milestones, detailed in the “WBS and Key Milestones” document: M1 Project Kick-off Complete → M2 Planning Documents Approved → M3 Requirements Approved (Sprint Backlog Set) → M4 Design Approved → M5 Development Complete → M6 Testing Complete (DoD Met) → M7 Delivery Preparation Complete → M8 Project Closure.

This phase delivers four planning documents: ① Team Meeting Minutes, ② Project Charter, ③ WBS and Key Milestones, ④ Project Gantt Chart.

8. Approvals

The following members confirm and approve this Project Charter:

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Cao Yang | Project Manager |  | 2026-09-20 |
| Chen Shuai | Business/Requirements Lead + Scribe |  | 2026-09-20 |
| Zhang Runze | Technical Lead |  | 2026-09-20 |
| Zhou Kunpeng | Scheduling Lead |  | 2026-09-20 |